CS-AML

Sprint & Milestone Plan v0.1

Engineering Delivery Baseline for MVP 0.1

Delivery axiom Deliver vertical, reviewable investigation capabilities. Sprint completion is not measured by isolated component output if the end-to-end analytical chain remains broken.

| Field | Baseline |
| --- | --- |
| Status | Planning baseline for MVP 0.1 |
| Planning cadence | 2-week sprint baseline; capacity-adjustable |
| Primary objective | Reach a releasable two-analyst end-to-end investigation workflow |
| Source documents | PRD v0.1; SRS v0.1; MVP Engineering Breakdown v0.1; Technical Stack & Repository Specification v0.1 |

# 1. Purpose and Planning Principles

This plan converts the approved MVP engineering breakdown into an executable sprint and milestone sequence. It defines delivery order, dependencies, parallel work, exit criteria, review checkpoints, release evidence, and decision gates. It does not replace the SRS or backlog; it governs how those requirements are delivered and verified.

## 1.1 Planning principles

Vertical slice over layer completion: each sprint SHOULD produce an analyst-visible capability where feasible.

Security, authorization, provenance, and audit are built into each slice; they are not deferred to a hardening sprint.

Canonical data and evidence integrity take precedence over derived search/graph convenience.

Every sprint MUST preserve traceability from SRS requirement to story/task/test evidence.

A milestone is accepted only when its exit criteria pass, not when its tickets are merely closed.

Unresolved high-severity security or data-integrity defects block promotion to the next release milestone.

Sprint dates are planning aids; dependency order and release gates are normative for this baseline.

## 1.2 Assumed team shape

This baseline assumes a small product engineering team. The sequence remains valid for a smaller or larger team, but parallelization should be adjusted.

| Role | Indicative Capacity | Primary Responsibilities |
| --- | --- | --- |
| Tech Lead / Backend | 1 | Architecture, domain model, security-sensitive backend, code review |
| Backend Engineer | 1-2 | Django modules, API, audit, async jobs, tests |
| Frontend Engineer | 1 | React analyst workspace, graph/timeline/value-flow UX |
| QA / Security-minded Engineer | 0.5-1 | Acceptance tests, negative authorization tests, release evidence |
| Product / Domain Lead | 0.5 | Acceptance, typology/methodology fidelity, pilot scenario |
| Ops / Platform | 0.25-0.5 | CI/CD, deployment, backup/restore, observability |

# 2. Delivery Cadence and Milestone Model

The baseline uses Sprint 0 followed by eight two-week delivery sprints. Each sprint closes one delivery increment or a coherent portion of it. Milestones M0-M4 provide broader product checkpoints.

| Milestone | Target State | Covered Sprints | Exit Meaning |
| --- | --- | --- | --- |
| M0 — Foundation Ready | Secure deployable skeleton | Sprint 0 | Team can develop against stable repo, CI, DB, evidence storage, audit and OIDC baseline. |
| M1 — Governed Case Workspace | Case + access + evidence intake usable | Sprints 1-2 | Team can open a compartmentalized case and preserve evidence with provenance. |
| M2 — Investigation Core | Entity/relationship/timeline/value-flow chain usable | Sprints 3-4 | Team can model subjects, assets, chronology and value movement with uncertainty preserved. |
| M3 — Analytical Intelligence | Typology/hypothesis/assessment + search/graph usable | Sprints 5-6 | Team can reason, test competing explanations, and navigate the investigation coherently. |
| M4 — MVP Release Candidate | Reviewed intelligence product + operational readiness | Sprints 7-8 | Full case-to-approved-product pilot passes release gate with restore, authorization and audit evidence. |

# 3. Sprint Overview

| Sprint | Theme | Epic Scope | Primary Deliverable | Milestone |
| --- | --- | --- | --- | --- |
| Sprint 0 | Engineering Foundation | E0 + E1 bootstrap | Repo, CI/CD, PostgreSQL, evidence store, audit substrate, OIDC skeleton | M0 |
| Sprint 1 | Identity + Governed Case Workspace | E1 + E2 partial | RBAC/case membership, protected source, case register, charter, basic activity |  |
| Sprint 2 | Workflow + Evidence Intake | E2 remainder + E3 | Gates/tasks, source register, immutable evidence, hash, extracts, lineage | M1 |
| Sprint 3 | Entities + Relationships | E4 | Entity registry, identifiers, matching, merge/unmerge, relationships, ownership/control, assets |  |
| Sprint 4 | Timeline + Follow-the-Value | E5 | Events/timeline, ValueFlow, multi-leg chains, uncertainty classes, flow visualization | M2 |
| Sprint 5 | Typology + Hypothesis + Assessment | E6 | Indicators, typology worksheet, competing hypotheses, gaps, confidence assessment |  |
| Sprint 6 | Search + Investigation Graph | E7 | Permission-aware search, facets, graph projection, provenance side panel | M3 |
| Sprint 7 | Intelligence Product + Review + Dissemination | E8 | Products, evidence index, peer review, corrections, approvals, export/referral, sharing log |  |
| Sprint 8 | Operational Release | E9 + full regression | Retention, backup/restore, hardening, E2E pilot, release evidence and remediation | M4 |

# 4. Dependency and Critical Path

The following chain represents the minimum critical path for MVP. Parallel work may occur around it, but breaking this sequence creates rework or weakens verification.

Critical path Foundation → Authorization → Case → Evidence → Entity/Relationship → Timeline/ValueFlow → Typology/Hypothesis/Assessment → Product/Review/Dissemination → Operational Release

| Dependency | Why It Exists | Can Parallelize? |
| --- | --- | --- |
| E0 → all | Shared repository, migrations, storage, audit and deployment baseline. | Only design/UX spikes may precede completion. |
| E1 → E2/E3/E7/E8 | Object access and compartmentalization must exist before sensitive case data. | E1 backend and E2 UI scaffolding may overlap. |
| E2 → E8 | Review/dissemination depends on case owner, status and lifecycle governance. | Product templates can be designed earlier. |
| E3 → E4/E6/E8 | Entities, analysis and products need evidence/provenance. | Schema work can overlap; production use cannot. |
| E4 → E5/E7 | Timeline/value-flow/graph require canonical entities and relationships. | Graph UI prototype may use fixtures. |
| E5 → E6 | Typology and hypotheses rely on structured events/flows. | Catalogue browser can be built early. |
| E6 → E8 | Products should contain reviewed assessments, alternatives, gaps and confidence. | Template engine may start early. |
| E8 → M4 | Release objective is reviewed, approved intelligence product. | Ops work proceeds continuously. |

# 5. Sprint-by-Sprint Delivery Plan

## 5.1 Sprint 0

Sprint goal: Create a reproducible, secure engineering foundation that all later vertical slices can depend on.

### Committed scope

ST-E0-01 Repository and service skeleton

ST-E0-02 Canonical PostgreSQL baseline

ST-E0-03 Evidence object storage baseline

ST-E0-04 Audit event substrate

ST-E1-01 OIDC login and session policy (bootstrap)

### Parallel work

Frontend shell and design tokens

Initial database/domain migration conventions

CI lint/unit/security scan wiring

### Sprint exit criteria

Fresh checkout runs locally with documented command

CI passes lint + unit tests

DB migrations apply to empty database

Evidence original cannot be overwritten by analyst path

Material create/update action produces immutable audit event

OIDC development login path works

### Required sprint evidence

CI run link/log

Migration test result

Evidence overwrite negative test

Audit event sample

Environment/bootstrap documentation

## 5.2 Sprint 1

Sprint goal: Establish governed access and the first usable case workspace.

### Committed scope

ST-E1-01 OIDC login and session policy (complete)

ST-E1-02 Role and case membership authorization

ST-E1-03 Protected-source compartment

ST-E2-01 Case register and creation

ST-E2-02 Investigation Charter

ST-E2-05 Case activity timeline (initial)

### Parallel work

Frontend case shell

Authorization test matrix

Protected-source UX and redaction design

### Sprint exit criteria

Unauthorized case access fails in API, not only UI

Protected source identity hidden from routine analyst

Case cannot activate without owner/purpose/question

Charter versioning works

Case creation/scope change appear in activity

### Required sprint evidence

Negative authorization tests

Protected-source compartment test

Case activation validation test

Charter version/audit test

## 5.3 Sprint 2

Sprint goal: Complete case governance and establish evidence-to-citation chain.

### Committed scope

ST-E2-03 Lifecycle gates G0-G6

ST-E2-04 Tasks and assignments

ST-E3-01 Source register

ST-E3-02 Original evidence ingestion

ST-E3-03 Hash/integrity verification

ST-E3-04 Evidence extracts and citations

ST-E3-05 Derivative lineage

ST-E3-06 Reliability and credibility ratings

### Parallel work

Upload/preview UI

Evidence metadata forms

Gate policy configuration

### Sprint exit criteria

Controlled case transition blocked without required gate

Source provenance minimum enforced

Evidence original preserved and hashed

Extract traces to parent evidence location

Derivative traces to original

Source reliability and information credibility are separate

### Required sprint evidence

Gate negative test

Evidence hash re-verification

Lineage test

Source rating test

M1 review demonstration

## 5.4 Sprint 3

Sprint goal: Build reusable identity, relationship, ownership/control and asset model.

### Committed scope

ST-E4-01 Entity registry

ST-E4-02 Aliases and identifiers

ST-E4-03 Candidate entity matching

ST-E4-04 Merge and unmerge

ST-E4-05 Relationships, ownership and control

ST-E4-06 Asset registry

### Parallel work

Entity search UX

Matching normalization rules

Relationship vocabulary seed

### Sprint exit criteria

Same entity can be reused across authorized cases

Conflicting identifiers coexist with provenance

Candidate match explains similarities/conflicts

Merge is evidence-backed and reversible

Relationship edge traces to evidence

Ownership/control/use remain separate

### Required sprint evidence

Merge/unmerge regression

Duplicate-name false merge test

Relationship provenance test

Asset attribution test

## 5.5 Sprint 4

Sprint goal: Make chronology and follow-the-value analysis operational.

### Committed scope

ST-E5-01 Events and temporal precision

ST-E5-02 Visual timeline

ST-E5-03 ValueFlow canonical model

ST-E5-04 Multi-leg flow builder

ST-E5-05 Flow visualisation

### Parallel work

Timeline UI

Flow builder UX

Export visual semantics

### Sprint exit criteria

Approximate dates remain approximate

Timeline respects object permissions

Every flow has one of four mandatory classes

Unknown value is not converted to zero

Multi-leg chain preserves per-leg evidence

Flow class remains visible in screenshot/export without color alone

### Required sprint evidence

Temporal precision tests

Flow class validation

Multi-leg lineage test

M2 investigation demonstration

## 5.6 Sprint 5

Sprint goal: Complete the analytical reasoning chain from indicator to confidence-rated assessment.

### Committed scope

ST-E6-01 Typology catalogue browser

ST-E6-02 Indicator capture

ST-E6-03 Typology match worksheet

ST-E6-04 Competing hypotheses

ST-E6-05 Intelligence gaps

ST-E6-06 Assessment and confidence

### Parallel work

Catalogue import/versioning

Hypothesis matrix UX

Assessment editor

### Sprint exit criteria

Catalogue version recorded in case analysis

Indicators link to evidence and do not equal proof

Typology match requires analyst rationale

Pilot supports at least two plausible hypotheses

Gaps remain explicit

Assessment traces backward to evidence with confidence basis

### Required sprint evidence

Typology version test

Hypothesis support/contradiction test

Assessment provenance traversal

Confidence validation

## 5.7 Sprint 6

Sprint goal: Add permission-aware discovery and graph exploration without creating a second source of truth.

### Committed scope

ST-E7-01 Permission-aware global search

ST-E7-02 Faceted case search

ST-E7-03 Investigation graph

### Parallel work

Search indexing tuning

Graph layout/filters

Authorization leakage testing

### Sprint exit criteria

Unauthorized objects never appear in result counts/snippets

Search result opens canonical object

Graph edge opens canonical relationship and evidence

Graph/search projection can be rebuilt

Graph does not promote inferred edge to verified relationship

### Required sprint evidence

Search leakage test

Graph provenance test

Projection rebuild test

M3 analyst workflow demonstration

## 5.8 Sprint 7

Sprint goal: Turn assessments into independently reviewed, versioned and controlled intelligence products.

### Committed scope

ST-E8-01 Intelligence product templates

ST-E8-02 Evidence index generation

ST-E8-03 Peer review workflow

ST-E8-04 Corrections and supersession

ST-E8-05 Dissemination approval and export

ST-E8-06 Referral package and sharing log

### Parallel work

Report rendering/export

Review UX

Export minimization/redaction rules

### Sprint exit criteria

Product has author/reviewer/classification/version

Key findings have evidence index

Independent review enforced where required

Post-approval change creates new version

External export blocked before approval

Sharing log immutable to ordinary analyst

### Required sprint evidence

Peer-review separation test

Evidence index trace test

Export approval negative test

Version supersession test

Referral package sample

## 5.9 Sprint 8

Sprint goal: Reach operational release readiness and prove MVP end-to-end.

### Committed scope

ST-E9-01 Controlled vocabulary admin

ST-E9-02 Retention policy engine

ST-E9-03 Backup and restore

ST-E9-04 Operational hardening

ST-E9-05 MVP end-to-end release test

### Parallel work

Security regression

Runbook completion

Pilot data preparation

Known limitations review

### Sprint exit criteria

Retention preview/hold works

Backup/restore succeeds with hash validation

Production hardening baseline passes

Full two-analyst pilot completes case-to-approved-product

Mandatory P0 SRS passes or has explicitly accepted exception

No open critical/high release-blocking defect

### Required sprint evidence

Restore test record

Security regression report

SRS traceability matrix

Two-analyst pilot record

Known limitations/accepted exceptions

M4 release sign-off

# 6. Milestone Acceptance Reviews

| Milestone | Review Participants | Mandatory Demonstration | Decision |
| --- | --- | --- | --- |
| M0 | Tech Lead, Ops, QA | Clean checkout → local run → CI → migration → evidence upload → audit → login | Proceed / remediate foundation |
| M1 | Product, Domain Lead, Security/QA | Create restricted case → charter → gate/task → source → evidence → extract/lineage | Proceed / narrow scope / remediate governance |
| M2 | Product, Analysts, QA | Evidence → entities → relationships/assets → timeline → multi-leg value flow | Proceed / correct domain model |
| M3 | Product, Analysts, Reviewer | Typology → competing hypotheses → gaps → assessment → search/graph traversal | Proceed / correct analytical UX |
| M4 | Product Owner, Reviewer, Security/Ops, QA | Full two-analyst case → approved intelligence product → controlled export → restore verification | Release / conditional release / no release |

# 7. Quality and Release Gates

## 7.1 Continuous gates in every sprint

Unit and integration tests for new domain behavior.

Negative authorization tests for new protected objects/endpoints.

Audit event verification for material state changes.

Migration forward test against clean and prior schema baseline.

No sensitive evidence content in routine logs, traces, or error responses.

Acceptance criteria demonstrated using realistic fixtures, not only mocked objects.

Updated traceability from SRS/feature ID to implementation and test evidence.

## 7.2 Release-blocking defect classes

| Severity | Examples | Release Treatment |
| --- | --- | --- |
| Critical | Authorization bypass; source identity exposure; evidence corruption; unrecoverable DB/evidence mismatch | Immediate block |
| High | Incorrect merge/unmerge; direct/reconstructed flow confusion; export without approval; broken audit history | Block M4 until fixed or formally waived by accountable authority |
| Medium | Workflow defect with safe workaround; non-critical UI/accessibility issue | May release with documented limitation and owner/date |
| Low | Cosmetic or minor usability issue | Backlog; does not block release |

# 8. Sprint Ceremonies and Decision Rhythm

| Cadence | Purpose | Required Output |
| --- | --- | --- |
| Sprint Planning | Confirm committed stories against capacity/dependencies | Sprint goal, committed scope, risks |
| Daily / async check-in | Surface blockers and security/data-integrity concerns early | Blocker log / owner |
| Mid-sprint technical review | Validate architecture/domain decisions before they harden | ADR or implementation adjustment |
| Sprint Review | Demonstrate analyst-visible vertical capability | Acceptance evidence + stakeholder notes |
| Sprint Retrospective | Improve delivery process | 1-3 concrete process actions |
| Milestone Review | Decide whether next dependency layer is safe to start | Go / conditional go / no-go record |

# 9. Epic-to-Sprint Traceability

| Epic | Primary Sprint(s) | Milestone | Key Release Evidence |
| --- | --- | --- | --- |
| E0 Foundation | 0 | M0 | CI, migrations, storage, audit, environment bootstrap |
| E1 Identity/Access | 0-1 | M0/M1 | OIDC, ACL negative tests, protected-source test |
| E2 Case Workflow | 1-2 | M1 | Case/charter/gates/tasks/activity demonstration |
| E3 Evidence Intake | 2 | M1 | Hash, provenance, extract, lineage evidence |
| E4 Entity/Relationship | 3 | M2 | Merge/unmerge, relationship provenance, asset attribution |
| E5 Timeline/ValueFlow | 4 | M2 | Temporal precision, four-class flow export |
| E6 Analytical Reasoning | 5 | M3 | Hypothesis matrix, typology version, assessment trace |
| E7 Search/Graph | 6 | M3 | Leakage test, graph provenance, rebuild test |
| E8 Products/Review/Dissemination | 7 | M4 | Review separation, evidence index, approved export, sharing log |
| E9 Operations/Release | 8 | M4 | Retention, restore, hardening, full pilot and traceability matrix |

# 10. Capacity Adjustment and Scope Change Rules

If actual team capacity differs from the baseline, preserve dependency order and milestone exit criteria. Adjust sprint count rather than compressing critical security, evidence, review, or restore work.

If capacity is lower: split a sprint by vertical outcome; do not split security from the feature it protects.

If capacity is higher: parallelize frontend/backend/test work inside the same epic or begin non-dependent next-sprint scaffolding.

P1/P2 features SHALL NOT enter MVP sprints if they jeopardize P0 exit criteria.

A new requirement affecting canonical data, authorization, provenance, value-flow semantics, or dissemination requires impact review against SRS and architecture.

Any scope cut from P0 requires explicit product-owner acceptance and must appear in Known Limitations / Accepted Exceptions.

# 11. MVP Release Evidence Package

SRS traceability matrix with implementation status and linked test evidence.

Two-analyst end-to-end pilot record from case creation to approved intelligence product.

Role/object-level authorization test results, including negative tests.

Protected-source compartment verification.

Evidence hash and derivative-lineage verification.

Entity merge/unmerge test record.

Value-flow class persistence test across DB/API/UI/export.

Typology/hypothesis/assessment provenance demonstration.

Peer-review separation and dissemination-approval test.

Backup/restore test with evidence hash validation.

Known limitations and formally accepted exceptions.

Release sign-off and version/build identifiers.

# 12. Canonical End-to-End Release Scenario

Analyst A authenticates through OIDC and creates a restricted case with an investigation question and charter.

Case owner assigns Analyst B as reviewer but not author and records lifecycle gate requirements.

Analyst A registers two sources, uploads evidence, verifies hashes, creates extracts, and records source reliability / information credibility separately.

Analyst A creates entities and identifiers, reviews a duplicate candidate, performs an evidence-backed merge, and verifies unmerge reversibility.

Analyst A records ownership/control relationships and an asset, each linked to evidence.

Analyst A creates events and a timeline, then builds a multi-leg value flow containing at least one documented and one reconstructed leg.

Analyst A maps indicators and counter-indicators to a versioned typology and records at least two plausible competing hypotheses.

Analyst A records unresolved intelligence gaps and writes a confidence-rated assessment traceable back to evidence.

Analyst A uses permission-aware search/graph to navigate the case; no unauthorized object is exposed.

Analyst A generates an intelligence product and evidence index. Analyst B independently reviews and requests one change before approval.

After approval, the case owner creates a dissemination record and exports a minimized referral package. The sharing log records recipient, version, purpose and restrictions.

Operations restores the release candidate dataset from backup and verifies evidence hashes and key canonical object links.

Release decision rule MVP 0.1 is releasable only when this scenario passes end-to-end, mandatory P0 SRS requirements are verified, and no unresolved Critical or release-blocking High defect remains.

# 13. Post-MVP Planning Boundary

The following items remain outside MVP 0.1 unless promoted through formal scope change: dedicated OpenSearch; Neo4j/Memgraph; OCR/entity extraction automation; OpenAleph/OpenSanctions/GraphSense integrations; AI assistant; federation/partner workspace; advanced beneficial-ownership calculations; network metrics; Kubernetes; microservices; event bus. Their planning begins only after M4 evidence is reviewed and operational pain points justify the added complexity.

# Annex A — Sprint Planning Checklist

Sprint goal maps to one analyst-visible outcome.

All committed stories satisfy Definition of Ready.

Dependencies from prior sprint are accepted, not merely coded.

Security/privacy/provenance tests are included in estimates.

Acceptance dataset/fixtures are available.

Traceability IDs are attached to stories/tasks/tests.

Release evidence owner is assigned.

Known risks and fallback plan are visible.

# Annex B — Sprint Review Checklist

Demonstrate capability using realistic investigation fixtures.

Show at least one negative authorization or misuse test.

Show provenance/audit path for newly created material records.

Review open defects by severity.

Confirm milestone exit criteria if applicable.

Record stakeholder acceptance or remediation actions.

# Annex C — Milestone Decision Record Template

| Field | Record |
| --- | --- |
| Milestone |  |
| Date |  |
| Build/version |  |
| Participants |  |
| Exit criteria result |  |
| Critical/high defects |  |
| Accepted exceptions |  |
| Decision | GO / CONDITIONAL GO / NO-GO |
| Required remediation |  |
| Approver |  |